FINAL PROGRAM RECONCILIATION CONTROL

CTA LCSW California Law & Ethics
Exam Preparation Program

Stage 5A Final Program Reconciliation & Handoff Readiness Register

CONTENT PACKAGE NOT YET READY FOR DAVID HANDOFF

CTA-EP-002 | Version 1.0 | August 6, 2026

Teaching Clinicians How to Think.

MATERIAL COMPLETION FINDING Stage 4 closed the three cumulative examination forms, but the complete learner program is not yet assembled. The active build package contains the LCSW/ASW license-specific module, five LCSW-first expansion chapter packages, and the cumulative examination system. It does not yet contain nine final LCSW Candidate Edition workbooks, the complete 45-chapter assessment/rationale set, the reconciled LCSW master flashcard system, six LCSW toolkits, or completed private-staging evidence. A final David ZIP would therefore be incomplete and must not be issued.

# Document Control

| Field | Controlling entry |
| --- | --- |
| Formal program | CTA LCSW California Law & Ethics Exam Preparation Program |
| Public display title | LCSW California Law & Ethics Exam Preparation |
| Program code | CTA-EP-002 |
| Offer | $199 launch/current price ¦ Six months of access |
| Classification | Self-paced exam preparation ¦ No CE credit, CE evaluation, or certificate |
| Audience | California ASWs and other eligible LCSW applicants preparing for the California LCSW Law and Ethics Examination |
| Current official boundary | The California Law and Ethics Examination is separate by license type; the later ASWB Clinical Examination is a separate examination and CTA product |
| Currentness baseline | Official BBS laws/regulations, applicant/examination pages, advertising guidance, and law-change materials rechecked August 6, 2026 |
| Stage 4 status | Cumulative examinations complete: 200 released items, 24 protected reserves, and 896 option rationales |
| Stage 5A status | Implementation controls created; full program handoff blocked by missing workbook, chapter-assessment, flashcard, toolkit, and staging assets |
| Final approver | Candice Fuimaono / CTA |

# 1. Executive Disposition

The course is not yet fully complete. The cumulative examination system is complete and internally controlled, but the program architecture also requires nine LCSW Candidate Edition workbooks covering 45 shared-core chapters, complete workbook/chapter assessment and rationale records, a unified LCSW flashcard Study Center, six LCSW-specific printable toolkits, learner orientation and closeout lessons, synchronized public/LMS copy, and private staging evidence. Only the learner orientation and implementation-copy controls are created in this Stage 5A package.

The five LCSW-first expansion chapters do not constitute five complete workbooks. They must be inserted into the authoritative nine-workbook backbone, and the remaining 40 chapters must still receive their required LCSW terminology, source, social-work ethics, scenario, assessment, rationale, remediation, and flashcard verification before the workbooks can be labeled LCSW Candidate Editions.

# 2. Reconciled Completion Status

| Component | Required volume | Status | Control note |
| --- | --- | --- | --- |
| LCSW/ASW license-specific module | 1 module + 25-question assessment + rationales + 25 cards | Complete content package | Available in active workspace |
| Five expansion chapters | 5 chapters × learner chapter, 17-question assessment, rationales, and 17 cards | Complete as chapter packages | Must be integrated into WB1, WB3, and WB7 |
| Practice Examination A | 50 released + 6 reserves; candidate, rationales, performance, controls | Content production closed | Current learner versions v1.1 / v1.1 / v1.0 |
| Practice Examination B | 50 released + 6 reserves; candidate, rationales, performance, controls | Content production closed | Current learner versions v1.2 / v1.2 / v1.1 |
| Comprehensive Final | 100 released + 12 reserves; candidate, rationales, performance, controls | Content production closed | Current learner versions v1.2 / v1.2 / v1.1 |
| Programwide cumulative QA | 224 records / 896 option rationales | Complete | Zero exact/normalized duplicate questions in final protected pool |
| Start Here and orientation | 1 learner file | Completed in Stage 5A | Use the companion v1.0 file |
| LMS implementation package | 1 internal control | Completed in Stage 5A | Private implementation and evidence not executed |
| Website/catalog/checkout/FAQ/LMS copy | 1 internal copy-control file | Completed in Stage 5A | Do not publish until remaining content gates close |
| Nine LCSW Candidate Edition workbooks | 9 workbooks / 45 chapters | NOT COMPLETE | Authoritative final files not present in active build package |
| Workbook/chapter assessment system | 45 chapter records / complete candidate and rationale delivery | NOT COMPLETE | Only module and five expansion-chapter assessment packages are complete |
| LCSW master flashcard Study Center | Unified master and learner outputs | NOT COMPLETE | Only 110 newly produced module/expansion cards are available |
| Six LCSW learner toolkits | TK01-TK06 | NOT COMPLETE | LCSW-specific source review and regeneration required |
| Private staging and learner-view evidence | Desktop/mobile/download/quiz/security/rollback evidence | NOT EXECUTED | Required after David builds private staging |

# 3. Release-Blocking Gap Register

| Gap | Missing control | Severity | Required closure action |
| --- | --- | --- | --- |
| G-001 | Nine full LCSW workbooks | Critical | Mount the authoritative nine source workbooks; integrate the five expansion chapters; replace all LMFT/AMFT identity and profession rules; issue nine LCSW Candidate Editions. |
| G-002 | Remaining 40 shared-core chapters | Critical | Complete sentence-level source/currentness, terminology, NASW ethics, scenario, and remediation verification for the 16 retain and 24 adapt chapters. |
| G-003 | Complete workbook assessment/rationale system | Critical | Finish the required LCSW disposition, adaptation, and synchronized rationales for the full 45-chapter assessment set; preserve answer-hidden and review editions. |
| G-004 | Master flashcard system | High | Reconcile source cards, the 25 module cards, and 85 expansion cards into one authoritative LCSW master; generate online Study Center and printable outputs. |
| G-005 | Six LCSW toolkits | High | Adapt and verify the six approved toolkit families for LCSW/ASW law, ethics, numbers, traps, study planning, and readiness. |
| G-006 | Catalog/pricing synchronization | High | Update the controlling catalogs from In Development to Completed for Implementation only after G-001 through G-005 close. |
| G-007 | Final handoff manifest and ZIP | Critical | Create only after every required current file is present, version reconciled, checksum frozen, and owner-approved for David. |
| G-008 | Private staging evidence | Critical | David builds private LMS/website/checkout; CTA tests learner access, downloads, quiz feedback, security, backup, and rollback. |
| G-009 | Final currentness recheck | Critical | Recheck BBS law changes, annual statutes/regulations, advertising, supervision, telehealth, examination materials, NASW ethics, and federal overlays within 30 days of public release. |

# 4. Current Owner-Approved Access Rule

NO EXAM-PREP ACCESS LOCKS This program is self-paced study, not continuing education. Do not require module completion, media completion, a minimum score, remediation completion, Practice A, Practice B, or another lesson before a learner can open or download learner-facing study materials. Display the recommended sequence as guidance only. Online quiz feedback may appear after submission, but downloadable workbooks, candidate forms, rationale files, performance tools, flashcards, and toolkits must not depend on another completion trigger.

All approved learner-facing downloads are available from enrollment for the six-month access term.

Candidate forms remain answer-hidden. Separate rationale documents may be accessible from enrollment but must clearly recommend completing and preserving a first attempt before review.

Online assessment questions may use post-submission answer feedback, scoring, and rationales without locking printable study resources.

Attempts are unlimited. An 80% score may be displayed only as a CTA study benchmark, never as an official passing score or access gate.

No CE evaluation, completion attestation, CE-hour field, certificate, or certificate trigger may be added.

# 5. Active Workspace Asset Snapshot

The active build workspace contains 37 current module, expansion, cumulative-examination, reserve, and Stage 4 control files. The table below is a reconciliation snapshot, not a final handoff manifest.

| ID | Category | Exposure | Filename | Status |
| --- | --- | --- | --- | --- |
| A-001 | License-specific module | Learner / study support | CTA_LCSW_Law_and_Ethics_EP_LCSW_Practice_Act_ASW_Professional_Identity_Social_Work_Ethics_and_California_Examination_Distinctions_Module_v1.0.docx | Content QA complete |
| A-002 | License-specific module | Learner / study support | CTA_LCSW_Law_and_Ethics_EP_License_Specific_Module_25_Question_Candidate_Assessment_v1.0.docx | Content QA complete |
| A-003 | License-specific module | Learner / study support | CTA_LCSW_Law_and_Ethics_EP_License_Specific_Module_25_Question_Controlled_Answer_Key_and_Detailed_Rationales_v1.0.docx | Content QA complete |
| A-004 | License-specific module | Learner / study support | CTA_LCSW_Law_and_Ethics_EP_License_Specific_Module_25_Card_Flashcards_and_Remediation_v1.0.docx | Content QA complete |
| A-005 | Expansion chapter package | Learner / study support | CTA_LCSW_Law_and_Ethics_EP_WB1_C4_Required_Disclosures_17_Card_Flashcards_and_Remediation_v1.0.docx | Content QA complete |
| A-006 | Expansion chapter package | Learner / study support | CTA_LCSW_Law_and_Ethics_EP_WB1_C4_Required_Disclosures_17_Question_Candidate_Assessment_v1.0.docx | Content QA complete |
| A-007 | Expansion chapter package | Controlled review | CTA_LCSW_Law_and_Ethics_EP_WB1_C4_Required_Disclosures_17_Question_Controlled_Answer_Key_and_Detailed_Rationales_v1.0.docx | Content QA complete |
| A-008 | Expansion chapter package | Learner / study support | CTA_LCSW_Law_and_Ethics_EP_WB1_C4_Required_Disclosures_LCSW_ASW_Candidate_Chapter_v1.0.docx | Content QA complete |
| A-009 | Expansion chapter package | Learner / study support | CTA_LCSW_Law_and_Ethics_EP_WB3_C2_Scope_of_Practice_vs_Scope_of_Competence_17_Card_Flashcards_and_Remediation_v1.0.docx | Content QA complete |
| A-010 | Expansion chapter package | Learner / study support | CTA_LCSW_Law_and_Ethics_EP_WB3_C2_Scope_of_Practice_vs_Scope_of_Competence_17_Question_Candidate_Assessment_v1.0.docx | Content QA complete |
| A-011 | Expansion chapter package | Controlled review | CTA_LCSW_Law_and_Ethics_EP_WB3_C2_Scope_of_Practice_vs_Scope_of_Competence_17_Question_Controlled_Answer_Key_and_Detailed_Rationales_v1.0.docx | Content QA complete |
| A-012 | Expansion chapter package | Learner / study support | CTA_LCSW_Law_and_Ethics_EP_WB3_C2_Scope_of_Practice_vs_Scope_of_Competence_LCSW_ASW_Candidate_Chapter_v1.0.docx | Content QA complete |
| A-013 | Expansion chapter package | Learner / study support | CTA_LCSW_Law_and_Ethics_EP_WB3_C5_Clinical_Supervision_Feedback_and_Accountability_17_Card_Flashcards_and_Remediation_v1.0.docx | Content QA complete |
| A-014 | Expansion chapter package | Learner / study support | CTA_LCSW_Law_and_Ethics_EP_WB3_C5_Clinical_Supervision_Feedback_and_Accountability_17_Question_Candidate_Assessment_v1.0.docx | Content QA complete |
| A-015 | Expansion chapter package | Controlled review | CTA_LCSW_Law_and_Ethics_EP_WB3_C5_Clinical_Supervision_Feedback_and_Accountability_17_Question_Controlled_Answer_Key_and_Detailed_Rationales_v1.0.docx | Content QA complete |
| A-016 | Expansion chapter package | Learner / study support | CTA_LCSW_Law_and_Ethics_EP_WB3_C5_Clinical_Supervision_Feedback_and_Accountability_LCSW_ASW_Candidate_Chapter_v1.0.docx | Content QA complete |
| A-017 | Expansion chapter package | Learner / study support | CTA_LCSW_Law_and_Ethics_EP_WB3_C6_Professional_Roles_and_Role_Clarification_17_Card_Flashcards_and_Remediation_v1.0.docx | Content QA complete |
| A-018 | Expansion chapter package | Learner / study support | CTA_LCSW_Law_and_Ethics_EP_WB3_C6_Professional_Roles_and_Role_Clarification_17_Question_Candidate_Assessment_v1.0.docx | Content QA complete |
| A-019 | Expansion chapter package | Controlled review | CTA_LCSW_Law_and_Ethics_EP_WB3_C6_Professional_Roles_and_Role_Clarification_17_Question_Controlled_Answer_Key_and_Detailed_Rationales_v1.0.docx | Content QA complete |
| A-020 | Expansion chapter package | Learner / study support | CTA_LCSW_Law_and_Ethics_EP_WB3_C6_Professional_Roles_and_Role_Clarification_LCSW_ASW_Candidate_Chapter_v1.0.docx | Content QA complete |
| A-021 | Expansion chapter package | Learner / study support | CTA_LCSW_Law_and_Ethics_EP_WB7_C3_Working_With_Diverse_Populations_17_Card_Flashcards_and_Remediation_v1.0.docx | Content QA complete |
| A-022 | Expansion chapter package | Learner / study support | CTA_LCSW_Law_and_Ethics_EP_WB7_C3_Working_With_Diverse_Populations_17_Question_Candidate_Assessment_v1.0.docx | Content QA complete |
| A-023 | Expansion chapter package | Controlled review | CTA_LCSW_Law_and_Ethics_EP_WB7_C3_Working_With_Diverse_Populations_17_Question_Controlled_Answer_Key_and_Detailed_Rationales_v1.0.docx | Content QA complete |
| A-024 | Expansion chapter package | Learner / study support | CTA_LCSW_Law_and_Ethics_EP_WB7_C3_Working_With_Diverse_Populations_LCSW_ASW_Candidate_Chapter_v1.0.docx | Content QA complete |
| A-025 | Practice A | Learner | CTA_LCSW_Law_and_Ethics_EP_Practice_Examination_A_Learner_Performance_and_Remediation_Workbook_v1.0.docx | Content QA complete |
| A-026 | Practice B | Learner | CTA_LCSW_Law_and_Ethics_EP_Practice_Examination_B_Learner_Performance_and_Remediation_Workbook_v1.1.docx | Content QA complete |
| A-027 | Comprehensive Final | Learner | CTA_LCSW_Law_and_Ethics_EP_Comprehensive_Final_Examination_Learner_Performance_and_Remediation_Workbook_v1.1.docx | Content QA complete |
| A-028 | Protected reserve | CTA internal only | CTA_LCSW_Law_and_Ethics_EP_Practice_Examination_A_6_Item_Controlled_Reserve_Set_v1.0.docx | Content QA complete |
| A-029 | Protected reserve | CTA internal only | CTA_LCSW_Law_and_Ethics_EP_Practice_Examination_A_6_Item_Controlled_Reserve_Answer_Key_and_Detailed_Rationales_v1.0.docx | Content QA complete |
| A-030 | Protected reserve | CTA internal only | CTA_LCSW_Law_and_Ethics_EP_Practice_Examination_B_6_Item_Controlled_Reserve_Set_v1.0.docx | Content QA complete |
| A-031 | Protected reserve | CTA internal only | CTA_LCSW_Law_and_Ethics_EP_Practice_Examination_B_6_Item_Controlled_Reserve_Answer_Key_and_Detailed_Rationales_v1.0.docx | Content QA complete |
| A-032 | Protected reserve | CTA internal only | CTA_LCSW_Law_and_Ethics_EP_Comprehensive_Final_Examination_12_Item_Controlled_Reserve_Set_v1.0.docx | Content QA complete |
| A-033 | Protected reserve | CTA internal only | CTA_LCSW_Law_and_Ethics_EP_Comprehensive_Final_Examination_12_Item_Controlled_Reserve_Answer_Key_and_Detailed_Rationales_v1.0.docx | Content QA complete |
| A-034 | Stage 4 control | CTA internal only | CTA_LCSW_Law_and_Ethics_EP_Stage4A_Protected_Cumulative_Item_Pool_and_Form_Assembly_Control_Register_v1.0.docx | Content QA complete |
| A-035 | Stage 4 control | CTA internal only | CTA_LCSW_Law_and_Ethics_EP_Stage4E_Final_Cumulative_Item_Master_Register_v1.0.docx | Content QA complete |
| A-036 | Stage 4 control | CTA internal only | CTA_LCSW_Law_and_Ethics_EP_Stage4E_Protected_24_Item_Reserve_Bank_and_Substitution_Control_Register_v1.0.docx | Content QA complete |
| A-037 | Stage 4 control | CTA internal only | CTA_LCSW_Law_and_Ethics_EP_Stage4E_Programwide_Duplicate_Exposure_and_Cumulative_QA_Closeout_Register_v1.0.docx | Content QA complete |

# 6. Stage 5 Controlled Build Sequence

| Stage | Controlled build | Exit condition |
| --- | --- | --- |
| Stage 5A | Reconciliation, Start Here, public/LMS copy, and implementation controls | THIS OUTPUT - complete; final handoff blocked |
| Stage 5B | Nine-workbook assembly and remaining 40-chapter LCSW verification | Nine final LCSW Candidate Edition workbooks and synchronized assessment/rationale records |
| Stage 5C | LCSW flashcard master and six toolkit regeneration | Unified master, online/print outputs, counts and source QA complete |
| Stage 5D | Final currentness, consistency, inventory, checksum, and David handoff ZIP | All files present; owner approves private implementation handoff |
| Stage 5E | Private staging, evidence, defect closure, backup/rollback, and release decision | Zero release-blocking defects and Candice written public-release approval |

# 7. Stage 5A Approval Record

| Approval field | Entry |
| --- | --- |
| Decision | ☐ Approve Stage 5A controls ☐ Corrections required |
| Completion finding | ☐ Confirm that the program is not yet ready for David handoff |
| Access rule | ☐ Approve no LMS access locks for learner-facing exam-preparation materials |
| Next build | ☐ Authorize Stage 5B nine-workbook assembly and 40-chapter verification |
| Approved by | Candice Fuimaono / CTA |
| Approval date | ____________________________ |
| Notes |  |