INTERNAL ADMIN RESOURCE

# LMFT and LCSW Exam Preparation Programs

Master Quality-Control Audit of 24 Student Workbooks

Audit Report v1.0  •  July 23, 2026

Publication Decision The workbook architecture is complete and instructionally strong, but the suite should remain on publication hold until assessment-key rebalancing, accessibility remediation, blueprint traceability, student/admin separation, and final source review are completed.

Scope: 12 California LMFT Clinical workbooks + 12 ASWB Clinical LCSW workbooks

# Executive Summary

This audit reviewed the latest available version of every student-facing workbook against CTA exam-preparation standards, current program crosswalks, official exam structures, source controls, assessment construction, accessibility, navigation, and publication readiness. The review found a complete 12-workbook architecture for both programs and strong learner-facing instructional design. It also found several system-level issues that should be corrected before any workbook is labeled v1.0 or released to students.

| Audit Measure | Result |
| --- | --- |
| Student workbooks reviewed | 24 |
| Current practice items | 255 |
| Workbooks with complete answer/rationale counts | 24 of 24 |
| Items keyed B | 160 of 255 |
| Items keyed D | 4 of 255 |
| Workbooks exceeding 3–5 objective standard | 19 of 24 |
| Workbooks missing explicit Chapter Summary | 16 of 24 |
| High-severity accessibility findings | 20 |
| Medium accessibility findings | 314 |
| Workbooks with page numbers | 24 of 24 |
| Workbooks with a table of contents | 0 of 24 |

## Overall Readiness Dashboard

| Category | Rating | Evidence | Decision |
| --- | --- | --- | --- |
| Program architecture | Strong | All 12 workbooks exist for each program and align with the planned topic architecture. | Proceed to evidence mapping. |
| Instructional content | Strong with revisions | All files include objectives, learner guidance, original questions, and full rationales. | Standardize chapter elements and student-facing controls. |
| Assessment integrity | Publication hold | Answer positions are highly predictable and complete assessment products are not yet built. | Rebalance and govern the item bank before release. |
| Accessibility | Publication hold | High-severity image-alt issues and broad table/heading remediation remain. | Complete a coordinated accessibility pass. |
| Source currency | Current baseline; signoff pending | Current ASWB and LMFT exam structures are accurately represented in the key overview workbooks. | Complete formal source and legal SME signoff. |
| Production readiness | Not ready for v1.0 | Draft, internal-reference, cover, metadata, TOC, and disclaimer inconsistencies remain. | Complete the revision plan in this report. |

# What Is Working Well

The full 12-workbook student architecture exists for both LMFT and LCSW programs.

All 24 workbooks contain learner guidance, learning objectives, original practice questions, and an answer-and-rationale section.

Question and rationale counts match in every workbook: 120 LMFT items and 135 LCSW items, including the 25-question LCSW mini-mock.

The writing consistently uses a coaching-oriented, exam-focused tone and emphasizes sequencing, safety, role clarity, assessment, and professional judgment.

Each program uses profession-specific reasoning rather than merely changing labels: systemic/relational framing for LMFT and person-in-environment, self-determination, access, advocacy, and social justice for LCSW.

No comments or tracked changes were found in the reviewed files, and all workbooks include page numbers.

The current ASWB and LMFT examination structures are accurately stated in the key strategy and mock workbooks.

# Audit Scope and Method

Compared workbook structure with CTA Exam Preparation Chapter Standards and CTA Assessment Development Standards.

Reviewed the latest version of each workbook; LCSW Workbook 1 v0.2 superseded v0.1.

Checked objective counts, required sections, question and rationale counts, option counts, correct-answer positions, disclaimers, internal production language, navigation fields, comments, tracked changes, images, and document metadata.

Ran an automated DOCX accessibility audit and interpreted table findings cautiously because some tables are layout/callout structures rather than data tables.

Compared program architecture with the LMFT Master Content Crosswalk and the Dual-Development Crosswalk.

Verified current exam facts against official ASWB, California BBS, and Pearson/BBS sources. Conducted a focused legal-content spot check rather than a substitute for final California counsel or subject-matter review.

# F-01  Correct-answer positions are highly predictable across the 255-question set.

CRITICAL  Assessment integrity

Evidence Overall keys: A 45 (17.6%), B 160 (62.7%), C 46 (18.0%), D 4 (1.6%). Among 223 four-option items, B is correct 134 times and D only 4 times. LCSW WB6 keys all 10 items as B; LCSW WB12 keys 23 of 25 as B.

Affected: All question sets; highest risk in LCSW WB6 and WB12.

Required action: Reorder or rewrite answer options and revalidate every rationale. Balance answer positions within each workbook and across mocks without creating a visible pattern.

Acceptance criterion: No workbook has a dominant answer position above 40% unless statistically justified; full banks pass answer-position and sequence-pattern checks.

Figure 1. The current answer-key distribution creates a learnable pattern unrelated to content mastery.

# F-02  The content workbooks do not yet constitute the complete CTA assessment system.

CRITICAL  Assessment product scope

Evidence The suite contains 120 LMFT questions and 135 LCSW questions. There are no 50-question workbook examinations, no 150-question LMFT simulation, and no 122-question LCSW simulation. LCSW WB12 contains a clearly labeled 25-question mini-mock.

Affected: Both programs.

Required action: Build tagged question banks, workbook examinations, and current-format full-length mock exams. Amend CTA standards so clinical mock lengths match each official exam rather than the 75-question Law and Ethics standard.

Acceptance criterion: Each program has an approved item bank, blueprint-weighted workbook exams, and at least two full-length simulations matching current official structure.

# F-03  The master crosswalk dashboards are administratively stale.

HIGH  Blueprint traceability

Evidence The LMFT crosswalk still reports 124 tasks as 'Mapped - Not Drafted.' The dual-program dashboard still reports 64 topics as 'Mapped - Not Drafted' and zero adaptations complete.

Affected: LMFT Master Content Crosswalk v1.0 and Dual-Development Crosswalk v1.2.

Required action: Update every task/topic with workbook, section heading, page evidence, question IDs, source status, reviewer, and completion status.

Acceptance criterion: All official LMFT tasks and all LCSW applied-knowledge statements have auditable evidence links and review status.

# F-04  The current drafts need a coordinated accessibility remediation pass.

HIGH  Accessibility

Evidence Automated audit identified 20 missing image-alt instances, 14 heading-level skips, and 300 table structures without marked header rows. The table count includes layout/callout tables and therefore requires classification, not blanket header assignment.

Affected: All 24 workbooks.

Required action: Add meaningful logo/image alt text, correct heading hierarchy, mark true data-table headers, convert or appropriately classify layout tables, verify reading order and hyperlinks, and rerun the audit.

Acceptance criterion: Zero high-severity accessibility findings and documented resolution of every remaining table finding.

# F-05  Workbook structure is not fully standardized to the CTA Exam Preparation Chapter Standards.

HIGH  CTA standards

Evidence Nineteen workbooks exceed the stated 3–5 objective standard; 16 lack an explicit Chapter Summary; one lacks an explicitly labeled memory aid. All have knowledge checks and detailed rationales.

Affected: Most workbooks.

Required action: Choose one consistent workbook standard: either reduce objectives and add summaries or formally revise the CTA standard for multi-topic workbooks. Add explicit high-yield memory and summary sections consistently.

Acceptance criterion: Every workbook passes a single approved structure checklist.

# F-06  Internal development language remains in student-facing drafts.

HIGH  Publishing controls

Evidence Twenty-two workbooks cite Shared Core/internal development files in student source notes; 20 contain a PUBLICATION CONTROL note. All 24 include 'For CTA review before publication.'

Affected: Most workbooks.

Required action: Create separate student and admin editions. Remove internal file names and production notes from the student edition; retain them in a controlled source register.

Acceptance criterion: Student files contain only learner-facing content and public source notes; admin files retain version and verification controls.

# Medium-Priority Findings

F-07  Cover naming and non-affiliation language are inconsistent.

Seventeen of 24 covers use the canonical program name; only 8 of 24 contain an explicit non-affiliation statement.

Action: Apply one cover template and one counsel-approved disclaimer to every workbook.

F-08  Final-publication navigation and file metadata are incomplete.

All 24 include page numbers, but none contains a table of contents. Four files list 'python-docx' as creator, and all retain a 2013 template creation date.

Action: Add a static or updateable TOC where appropriate, create accessible hyperlinks, set CTA author/title/subject metadata, and scrub template metadata.

F-09  Student files do not carry admin item metadata needed for quality control.

No Question ID, difficulty, primary concept, cognitive type, blueprint tag, source status, or item-review field appears in the current files.

Action: Move every item into a controlled admin question bank with IDs and tags; keep the student presentation clean.

F-10  One high-similarity item appears within the LCSW program.

LCSW WB11 Q10 and LCSW WB12 Q25 both use a clinic with long intake delays and lower completion among clients needing interpreters.

Action: Rewrite one item so the integrated mock tests transfer rather than recognition.

F-11  The LCSW practice mix is only partly aligned with the redesigned three- and four-option format.

Across 135 LCSW items, 32 use three options and 103 use four. The 25-question mini-mock uses a stronger three-option mix, but most workbook checks are exclusively four-option.

Action: Set an intentional option-format plan based on the current ASWB format, without inventing an unsupported exact percentage.

F-12  Current official baselines are correctly reflected, but final release still requires formal source signoff.

ASWB facts in WB1/WB12 match the 2026 guidebook. LMFT WB1 matches the current Pearson/BBS structure. Spot checks of LMFT WB6 and WB12 found cautious, source-aligned statements regarding child reporting, elder/dependent-adult reporting, duty to protect, Section 5150 authority, subpoenas, and privilege.

Action: Complete line-by-line clinical and California legal SME review and date-stamp the source register immediately before v1.0 publication.

# Official Source Verification

Verified Current Baselines ASWB Clinical workbooks use the August 3, 2026 structure: 122 total questions, 12 unscored, four hours, two 61-question sections, and content weights of 36% Values and Ethics, 32% Assessment and Planning, and 32% Intervention and Practice. The LMFT strategy workbook uses the current Pearson/BBS structure: 125 scored questions, 25 pretest questions, and 240 minutes.

## ASWB Examination Guidebook — 2026 Blueprints

Version/date: Published May 2026; exams on/after Aug. 3, 2026

Verified: Clinical exam: 122 total, 12 unscored, 110 scored; four hours; two 61-question sections; 36% Values and Ethics, 32% Assessment and Planning, 32% Intervention and Practice; three- and four-option questions.

Recheck: Before release and at least annually.

https://www.aswb.org/wp-content/uploads/2026/05/2026-Social-Work-Licensing-Exam-Guidebook-5.4.2026.pdf

## ASWB 2026 Exam Transition

Version/date: Current July 2026

Verified: Redesigned exams begin August 3, 2026; 122 total questions including 12 unscored.

Recheck: After launch and before marketing updates.

https://www.aswb.org/2026exams/

## California BBS LMFT Clinical Exam Page / Pearson Candidate Handbook

Version/date: BBS current page; Pearson handbook July 2026

Verified: LMFT Clinical is a separate required exam; current handbook lists 125 scored questions, 25 pretest questions, and 240 minutes.

Recheck: Before release and whenever Pearson/BBS updates the handbook.

https://www.bbs.ca.gov/exams/lmft.html

## California BBS Statutes and Regulations

Version/date: January 1, 2026 compilation

Verified: Current BBS statutory/regulatory baseline for LMFT practice and professional obligations.

Recheck: Immediately before release and after every California legislative/regulatory update.

https://www.bbs.ca.gov/pdf/publications/lawsregs.pdf

## California BBS Law and Regulation Updates

Version/date: Current web page

Verified: Publication and maintenance trigger for new statutes, regulations, and guidance.

Recheck: Quarterly during development; before every annual edition.

https://www.bbs.ca.gov/about/law_reg.html

# Program-Level Conclusions

## California LMFT Clinical Program

The 12-workbook architecture follows the six-domain content plan and preserves the intended systemic, relational, diagnostic, crisis, planning, treatment, and professional-practice lenses.

The master task crosswalk must be updated from “Mapped - Not Drafted” to evidence-based completion status with page and question links.

Future question banks and mocks must be weighted to the official domain distribution rather than treating each workbook equally.

Workbooks 6 and 12 require final, line-by-line California legal review and a dated source signoff before publication.

A full 150-question LMFT simulation should include 125 scored-style items plus 25 unscored-style items presented without identification.

## ASWB Clinical LCSW Program

The 12-workbook architecture addresses the 2026 Values and Ethics, Assessment and Planning, and Intervention and Practice content areas.

The 25-question mini-mock correctly scales the 36/32/32 blueprint to 9/8/8 questions, but it is not a full exam simulation.

Question development should intentionally use both three- and four-option items and should be governed at the bank level rather than left to workbook-by-workbook drift.

The full mock should reproduce the two-section structure, scheduled break rules, four-hour timing, and inability to return to the first section after submission.

After the redesigned exam launches on August 3, 2026, CTA should perform a post-launch source check before final publication and marketing.

# Recommended Revision and Production Plan

| Seq. | Workstream | Scope | Required Output | Gate |
| --- | --- | --- | --- | --- |
| 1 | Global template and student/admin split | All 24 workbooks | Standard cover, disclaimer, 3–5 objectives or approved revised standard, chapter summary, learner-only source notes, TOC/navigation, metadata. | Template QA approved. |
| 2 | Accessibility remediation | All 24 workbooks | Alt text, corrected heading hierarchy, classified data/layout tables, link/read-order review. | Zero high-severity findings. |
| 3 | Question-bank normalization | All 255 current items | Unique IDs, tags, balanced key positions, option-format plan, duplicate check, rationale revalidation. | Assessment QA report approved. |
| 4 | Blueprint evidence mapping | 124 LMFT tasks and 2026 LCSW Clinical applied-knowledge statements | Page/section/question/source evidence map with reviewer status. | 100% mapped and reviewed. |
| 5 | Clinical and legal SME review | All workbooks; focused review of LMFT WB6/WB12 and diagnosis/medication content | Signed source and accuracy review log. | No unresolved high-risk comments. |
| 6 | Assessment product build | Both programs | Workbook exams, expanded question banks, LMFT 150-question mocks, LCSW 122-question mocks, scoring/error-analysis tools. | Blueprint and psychometric QA complete. |
| 7 | Final production | All deliverables | Approved v1.0 DOCX/PDF student editions and admin masters. | Final render, accessibility, source, metadata, and version-control signoff. |

# v1.0 Publication Gate

☐ All 24 workbooks use the approved cover, naming, disclaimer, copyright, version, source-note, and metadata template.

☐ Every workbook passes the approved CTA structure checklist, including the chosen objective and chapter-summary standard.

☐ All 255 current items have unique IDs, blueprint tags, cognitive-level tags, revised answer-position balance, verified rationales, and reviewer signoff.

☐ No high-severity accessibility findings remain; data tables, layout tables, headings, images, reading order, and links are documented.

☐ The LMFT 124-task evidence map and LCSW 2026 applied-knowledge evidence map are complete.

☐ California legal and clinical subject-matter reviews are completed and dated.

☐ Full-length mocks and expanded question banks match current official exam structures and blueprints.

☐ Final DOCX and PDF editions are rendered page by page and approved before release.

# Appendix A — Workbook-Level Audit Summary

## LMFT Workbooks

| WB | Title | Status | Priority action |
| --- | --- | --- | --- |
| 1 | Exam Strategy and Clinical Reasoning | Revision Required | rebalance answer positions (B 7/10); complete accessibility remediation |
| 2 | Clinical Engagement, Intake, and Mental Status Assessment | Revision Required | reduce objectives to 3–5; add standard disclaimer; complete accessibility remediation; remove internal source references; move publication controls to admin file |
| 3 | Developmental, Psychosocial, and Diversity Assessment | Revision Required | reduce objectives to 3–5; add standard disclaimer; complete accessibility remediation; remove internal source references |
| 4 | Relational, Family-System, Trauma, and Strengths Assessment | Revision Required | reduce objectives to 3–5; add chapter summary; add standard disclaimer; complete accessibility remediation; remove internal source references |
| 5 | Diagnosis and Differential Diagnosis | Revision Required | reduce objectives to 3–5; add standard disclaimer; complete accessibility remediation; remove internal source references |
| 6 | Crisis, Abuse, and Safety | Revision Required | reduce objectives to 3–5; add chapter summary; add standard disclaimer; complete accessibility remediation; remove internal source references; complete California legal SME review |
| 7 | Planning, Progress, and Termination | Revision Required | rebalance answer positions (B 7/10); reduce objectives to 3–5; add chapter summary; complete accessibility remediation; remove internal source references |
| 8 | Family, Couple, Attachment, and Relational Interventions | Major Revision | rebalance answer positions (B 8/10); reduce objectives to 3–5; add chapter summary; complete accessibility remediation; remove internal source references |
| 9 | Trauma, Psychological, Behavioral, and Recovery Interventions | Revision Required | add chapter summary; complete accessibility remediation; remove internal source references |
| 10 | Developmental, Cultural, and Contextual Interventions | Revision Required | add chapter summary; complete accessibility remediation; remove internal source references |
| 11 | Theory, Groups, Referral, and Interdisciplinary Collaboration | Revision Required | reduce objectives to 3–5; add chapter summary; complete accessibility remediation; remove internal source references |
| 12 | California Legal, Ethical, and Professional Practice | Major Revision | rebalance answer positions (B 8/10); reduce objectives to 3–5; add chapter summary; add standard disclaimer; complete accessibility remediation; remove internal source references; complete California legal SME review |

## LCSW Workbooks

| WB | Title | Status | Priority action |
| --- | --- | --- | --- |
| 1 | ASWB Exam Strategy and Applied Reasoning | Revision Required | rebalance answer positions (B 7/10); complete accessibility remediation |
| 2 | Values, Ethics, Self-Determination, and Social Justice | Revision Required | reduce objectives to 3–5; add chapter summary; add standard disclaimer; complete accessibility remediation; remove internal source references |
| 3 | Human Development, Diversity, and Person-in-Environment | Revision Required | rebalance answer positions (A 7/10); reduce objectives to 3–5; add standard disclaimer; complete accessibility remediation; remove internal source references |
| 4 | Clinical Assessment, Interviewing, and Mental Status | Revision Required | reduce objectives to 3–5; add standard disclaimer; complete accessibility remediation; remove internal source references; move publication controls to admin file |
| 5 | Diagnosis, Medical Factors, and Psychopharmacology | Revision Required | reduce objectives to 3–5; add standard disclaimer; complete accessibility remediation; remove internal source references |
| 6 | Crisis, Abuse, and Risk Assessment | Major Revision | rebalance answer positions (B 10/10); reduce objectives to 3–5; add chapter summary; add standard disclaimer; complete accessibility remediation; remove internal source references |
| 7 | Treatment and Service Planning | Revision Required | reduce objectives to 3–5; add chapter summary; add standard disclaimer; complete accessibility remediation; remove internal source references |
| 8 | Clinical Interventions and Trauma-Informed Practice | Revision Required | rebalance answer positions (A 7/10); reduce objectives to 3–5; add chapter summary; add standard disclaimer; complete accessibility remediation; remove internal source references |
| 9 | Family, Couple, Group, and Parenting Interventions | Major Revision | rebalance answer positions (B 8/10); reduce objectives to 3–5; add chapter summary; add standard disclaimer; complete accessibility remediation; remove internal source references |
| 10 | Case Management, Advocacy, Resources, and Collaboration | Revision Required | add chapter summary; add standard disclaimer; complete accessibility remediation; remove internal source references |
| 11 | Practice Evaluation, Research, Supervision, and Administration | Major Revision | rebalance answer positions (B 8/10); reduce objectives to 3–5; add chapter summary; complete accessibility remediation; remove internal source references |
| 12 | Integrated Review and Mock Examination | Major Revision | retain as mini-mock; build separate 122-question full mock; rebalance answer positions (B 23/25); reduce objectives to 3–5; add chapter summary; add standard disclaimer; complete accessibility remediation; remove internal source references |

# Appendix B — Audit Totals and Interpretation Notes

Answer-position statistics evaluate test-construction pattern risk, not content accuracy. Rebalancing should preserve the one-best-answer logic and must include a complete rationale recheck.

The automated accessibility tool flags every table without a header marker. Many CTA callout boxes are built as one-cell layout tables; these should be classified and remediated appropriately rather than automatically treated as data tables.

The audit confirms structural and source baselines but does not replace licensed clinical, psychometric, accessibility, or California legal review.

This report did not modify the 24 workbook drafts. It establishes the controlled revision backlog for the next production phase.