# LMFT & LCSW Clinical Exam Preparation Programs

Self-Paced Online, Downloadable, and Multimedia Delivery Plan

Website Course Architecture  •  Printable Pathway  •  Video & Audio Curriculum

CTA Program Development Standard

Version 1.0 • July 2026

Internal Planning and Production Document

Governing Direction Both programs will be fully self-directed. A student may complete the entire program inside the CTA website, download and print the materials for paper study, or combine both methods. Video and audio instruction will function as the supportive instructor presence within the program.

# 1. Purpose and Final Delivery Model

This plan converts the completed LMFT and LCSW exam-preparation materials into a unified self-paced learning system. The design assumes no live teacher, cohort facilitator, or course administrator is required for instruction. CTA retains internal quality-control and question-bank administration functions, while the student experience remains guided, clear, and independent.

Big Idea The website should not merely store files. It should actively guide the student through a repeatable cycle of learning, practice, feedback, remediation, and simulated testing.

## Core delivery commitments

The complete program can be finished online without printing.

Every student-facing workbook and roadmap can also be downloaded and printed.

Online and paper pathways follow the same 12-workbook sequence and learning logic.

Question feedback teaches why the best answer is correct and why each distractor is weaker.

Video, audio, captions, and transcripts provide instructor-like coaching without requiring live instruction.

Form A and Form B remain controlled readiness simulations and are not treated as casual practice sets.

Internal master question banks, administrative item banks, use logs, and QC reports are never student-facing.

# 2. Three Supported Student Pathways

| Pathway | Student Experience | Primary Benefits | Required CTA Support |
| --- | --- | --- | --- |
| Fully Online | Read lessons on the website, answer questions online, receive scoring and controlled feedback, and complete Forms A and B through the course portal. | Immediate navigation, progress tracking, automatic scoring, accessible multimedia, and one-place study. | Responsive lesson pages, quiz engine, progress tracking, timed exam capability, captions, transcripts, and technical help. |
| Download and Print | Download workbooks, question banks, roadmaps, trackers, and permitted rationale guides. Complete materials by hand and self-score using released answer resources. | Paper annotation, reduced screen time, portable study, and familiar test-preparation habits. | Print-optimized files, clear file names, separate answer resources, and visible instructions for when to review rationales. |
| Hybrid | Watch or listen online, print selected workbooks, complete question banks online, and use paper trackers or notes. | Maximum flexibility and accessibility across home, work breaks, commuting, and travel. | Consistent numbering, matching online and printable content, downloadable audio, and synchronized release rules. |

# 3. Student Journey and Completion Logic

Both programs should present the same visible sequence. Students should always know what to do now, what unlocks next, and what evidence of completion they should produce.

| Stage | Student Action | Website Behavior | Completion Evidence |
| --- | --- | --- | --- |
| 1. Orient | Review the welcome lesson, program roadmap, study schedule, and exam-strategy orientation. | Mark orientation lessons complete and prompt the student to select a study pace. | Chosen 10-, 14-, or 18-week plan. |
| 2. Learn | Complete the assigned workbook and companion multimedia. | Display workbook lesson, downloads, video/audio, transcript, and key prompts. | Workbook completion check. |
| 3. Practice | Complete the associated 17-question bank without viewing answers. | Score the bank after submission; prevent answer display before submission. | Bank score and saved responses. |
| 4. Review | Study complete rationales and CTA Exam Strategies. | Release rationale feedback after submission or through a separate controlled lesson. | Missed-item notes and error classification. |
| 5. Remediate | Return to weak topics and repeat selected practice activities. | Link missed concepts to the relevant workbook section and micro-lesson. | Updated error log and remediation checklist. |
| 6. Simulate | Complete Form A, remediate, then complete Form B under timed conditions. | Use controlled timed-exam settings and delayed rationale release. | Simulation score, pacing notes, and readiness decision. |

Default Release Rule Students may revisit learning content at any time. Answer rationales should appear only after a question bank or simulation attempt is submitted. Form B should remain locked until Form A and the required remediation step are complete.

# 4. Website Course Architecture

Each profession should have its own course shell with the same navigation logic. Shared strategy videos may be reused, but all labels, workbook titles, question banks, and comprehensive forms must remain profession-specific.

| Course Area | Recommended Contents | Student-Facing? |
| --- | --- | --- |
| Start Here | Welcome video, how-to-use-the-program video, roadmap, schedule selector, printable checklist, technical guidance, and exam-prep disclaimer. | Yes |
| Core Strategy Library | FIRST/NEXT/BEST/MOST reasoning, assessment-versus-intervention sequencing, distractor elimination, pacing, error-log use, and anxiety-management recordings. | Yes |
| Workbooks 1–12 | One course section per workbook with workbook file, web lesson or reading page, companion media, 17-question bank, rationale lesson, and remediation prompt. | Yes |
| Comprehensive Form A | Readiness instructions, timed simulation, submission, score summary, delayed detailed rationales, and required remediation plan. | Yes |
| Comprehensive Form B | Final simulation, score summary, rationales, readiness interpretation, and final-week checklist. | Yes |
| Resource Library | Roadmap, error log, readiness tracker, printable study calendars, quick-reference sheets, transcripts, and downloadable audio. | Yes |
| CTA Internal Administration | Master spreadsheets, administrative banks, item-use logs, blueprint/QC reports, version history, and retired-item records. | No |

## Recommended workbook lesson template

| Order | Lesson Element | Function |
| --- | --- | --- |
| 1 | Workbook Overview | States the topic, why it matters, and how it appears on the exam. |
| 2 | Companion Video or Audio | Explains high-yield reasoning and common mistakes without reading the workbook aloud. |
| 3 | Workbook Content | Online reading page, downloadable Word/PDF copy, or both. |
| 4 | Completion Prompt | Asks the student to summarize key rules or decision points before testing. |
| 5 | 17-Question Bank | Tests the workbook topic with 5 Easy, 7 Moderate, and 5 Difficult items. |
| 6 | Rationale Review | Provides option-by-option explanations and CTA Exam Strategy after submission. |
| 7 | Remediation Check | Requires the student to classify misses and identify what to review. |

# 5. Online Assessment and Feedback Rules

Require submission before displaying correct answers or rationales.

Show the selected answer, correct answer, complete option-by-option rationale, and CTA Exam Strategy.

Allow students to review completed workbook banks after the first submitted attempt.

Preserve the original question ID internally, even when the ID is hidden from the student.

Record attempt date, score, time used, and item-level responses when the website supports it.

Avoid presenting a fixed CTA passing score as equivalent to an official licensing-exam standard.

Use readiness language such as developing, progressing, needs targeted review, and ready for final simulation.

## Workbook-bank feedback

Workbook banks are teaching assessments. Immediate post-submission feedback is appropriate because their purpose is to reinforce the workbook topic and strengthen reasoning.

## Comprehensive-form feedback

Forms A and B are simulation assessments. Students should first receive a score summary and domain-level performance profile. Detailed rationales should be released after the full attempt is complete so the student cannot use feedback from earlier questions to influence later answers.

| Control | Workbook Bank | Form A | Form B |
| --- | --- | --- | --- |
| Timing | Untimed or softly timed | Full simulation timing | Full simulation timing |
| Feedback | After submission | After full exam submission | After full exam submission |
| Retake | Allowed for remediation | One primary timed attempt; later review attempt may be allowed | Preserve as final readiness form; restrict casual retakes |
| Unlock Rule | After workbook completion | After all 12 workbooks and banks | After Form A remediation |
| Purpose | Teach and reinforce | Diagnose remaining gaps | Evaluate final readiness |

# 6. Downloadable and Printable Delivery

The printable pathway should be a first-class version of the program, not an afterthought. Students who print should be able to follow the same sequence without needing hidden instructions from the website.

| File Type | Student Use | Release Rule |
| --- | --- | --- |
| Student Roadmap and Study Schedule | Select pace, track progress, and plan simulations. | Available at enrollment. |
| Workbook Files | Read, annotate, and complete prompts. | Release all at once or sequentially by workbook. |
| 17-Question Banks | Complete on paper before reviewing answers. | Pair with each workbook; keep answer resources separate. |
| Answer and Rationale Resources | Self-score and study distractor reasoning. | Release after the associated bank is completed. |
| Forms A and B | Complete under printed simulated conditions. | Form A after the curriculum; Form B after remediation. |
| Trackers and Logs | Record misses, decision-rule errors, timing, and weak topics. | Available throughout the course. |

Print-Package Rule Never place an answer key immediately behind the student exam in the same downloadable file. Keep student questions and answer/rationale documents separate so students can simulate test conditions.

# 7. Multimedia Curriculum Strategy

Multimedia should provide the coaching presence that would otherwise come from a live instructor. The strongest format is a concise CTA-branded narrated slide video with captions, a transcript, and an audio-only version.

| Asset | Recommended Length | Purpose | Required Companion |
| --- | --- | --- | --- |
| Welcome Video | 4–6 minutes | Build confidence, explain the program promise, and set expectations. | Transcript and captions |
| Orientation / How-To Video | 8–12 minutes | Demonstrate the study cycle, navigation, downloads, scoring, and Form A/Form B sequence. | Transcript, captions, and quick-start sheet |
| Core Strategy Lesson | 8–15 minutes | Teach one reasoning skill through examples and verbal coaching. | Slides, transcript, captions, and MP3 |
| Workbook Companion Lesson | 6–12 minutes | Identify high-yield concepts, exam traps, and reasoning priorities for one workbook. | Transcript, captions, and optional MP3 |
| Rationale Coaching Clip | 3–6 minutes | Explain a recurring mistake pattern after a question bank or simulation. | Transcript and captions |
| Audio Review | 5–15 minutes | Support commuting, walking, and screen-free review. | Downloadable MP3 and matching transcript |

## Narration standard

Sound like a supportive exam coach speaking directly to one candidate.

Explain how to think, not merely what to memorize.

Use short clinical examples and verbalize why a tempting distractor is premature, incomplete, or outside the question asked.

Avoid reading workbook paragraphs or slide bullets word for word.

End each recording with one clear action the student should take next.

Use the same terminology as the workbooks and question rationales.

# 8. Recommended Core Recording Library

## Shared recordings for both programs

| # | Recording | Target Length | Primary Outcome |
| --- | --- | --- | --- |
| 1 | Welcome to the CTA Exam Success System | 4–6 min | Understand what the program includes and how confidence will be built. |
| 2 | How to Use the 12 Workbooks and Question Banks | 8–10 min | Follow the full learning-practice-review cycle. |
| 3 | How to Read FIRST, NEXT, BEST, and MOST Appropriate Questions | 10–12 min | Identify the task word and sequence the response. |
| 4 | Assessment, Intervention, Evaluation, and Follow-Up | 10–12 min | Separate information gathering from action and outcome review. |
| 5 | How to Eliminate Plausible but Premature Answers | 8–12 min | Reject answers that are clinically reasonable but mistimed. |
| 6 | How to Use Rationales and Build an Error Log | 8–10 min | Turn missed questions into targeted remediation. |
| 7 | How to Take Forms A and B Under Simulated Conditions | 8–10 min | Protect the diagnostic value of each comprehensive form. |
| 8 | Pacing, Decision Fatigue, and Test Anxiety | 10–12 min | Use practical pacing and recovery strategies during a long exam. |

## LMFT-specific recordings

| # | Recording | Primary Coaching Focus |
| --- | --- | --- |
| 1 | Thinking Relationally and Systemically | Identify patterns, reciprocal influence, context, and the treatment unit. |
| 2 | Clinical Evaluation and the Mental Status Examination | Gather enough information before selecting an intervention. |
| 3 | Diagnosis and Differential Diagnosis | Use duration, impairment, exclusions, and competing explanations. |
| 4 | Crisis and Safety Sequencing | Prioritize immediate danger, level of care, and stabilization. |
| 5 | Case Conceptualization and Treatment Planning | Connect assessment findings to measurable treatment direction. |
| 6 | Selecting Individual, Couple, Family, and Group Interventions | Match intervention level and modality to the clinical pattern. |
| 7 | California Legal and Ethical Reasoning | Recognize when legal or ethical obligations change the clinical sequence. |

## LCSW-specific recordings

| # | Recording | Primary Coaching Focus |
| --- | --- | --- |
| 1 | Applying Social Work Values and Ethics | Balance self-determination, dignity, safety, competence, and professional responsibility. |
| 2 | Person-in-Environment Reasoning | Integrate individual functioning, relationships, systems, culture, and resources. |
| 3 | Assessment, Diagnosis, and Planning | Sequence information gathering, formulation, and collaborative planning. |
| 4 | Crisis, Safety, Abuse, and Neglect | Distinguish assessment, protection, reporting, and stabilization priorities. |
| 5 | Intervention, Case Management, and Advocacy | Choose the intervention level that best addresses the stated barrier. |
| 6 | Collaboration and Interdisciplinary Practice | Clarify role, consent, information sharing, and coordinated action. |
| 7 | Three-Option and Four-Option Question Strategy | Use the available option set without assuming a missing fourth choice. |

Recommended Production Sequence Record the eight shared lessons first. They support both programs immediately. Then record the seven LMFT and seven LCSW profession-specific lessons. Workbook-by-workbook companion videos can be added as a second multimedia phase.

# 9. Workbook Companion Media

A short companion recording for each workbook would create a consistent instructor presence throughout the program. These recordings should preview the exam logic of the topic and identify the mistakes students are most likely to make.

| Segment | Suggested Time | Content |
| --- | --- | --- |
| Opening | 30–45 sec | State the workbook topic and why it matters on the exam. |
| Three High-Yield Ideas | 3–5 min | Explain the most testable distinctions and sequencing rules. |
| Common Exam Traps | 2–3 min | Name distractor patterns and premature actions. |
| Mini Scenario | 1–2 min | Model how to reason through one short original example. |
| Study Direction | 30–60 sec | Tell the student what to notice while completing the workbook and bank. |

# 10. Multimedia Production and Accessibility Standard

| Area | CTA Standard |
| --- | --- |
| Visual Format | Use clean CTA-branded slides, limited text, strong contrast, and one central idea per slide. |
| Audio | Use clear, consistent volume; remove background noise; speak at a natural instructional pace. |
| Captions | Provide accurate synchronized captions for every video. |
| Transcript | Provide an editable, downloadable transcript that matches the final recording. |
| Audio-Only File | Export core strategy and workbook companion recordings as MP3 files when practical. |
| Playback | Allow pause, replay, volume control, and variable playback speed when the platform supports it. |
| Navigation | Do not require watching a video to locate the printable workbook or transcript. |
| Accessibility | Use descriptive links, keyboard-friendly navigation, readable headings, alt text, and accessible tables. |
| Updates | Maintain the script, slides, transcript, captions, MP3, and video as one controlled version set. |

## Recording package per lesson

Final narration script

CTA-branded slide deck

Video file

Caption file or platform captions

Accessible transcript

Audio-only MP3 when appropriate

Source and review record

Version number and publication date

# 11. Student Support Without a Teacher

The program does not need a live instructor, but students still need clear self-service support. The website should separate technical support from individualized clinical or licensing advice.

| Support Need | Recommended Solution |
| --- | --- |
| How to begin | Quick-start lesson, roadmap, schedule selector, and visible Start Here button. |
| How to study | Short orientation video and printable CTA Study Cycle checklist. |
| Why an answer was missed | Complete rationales, CTA Exam Strategy, and error-log prompts. |
| What to review next | Domain summaries, workbook links, and remediation checklists. |
| Technical problem | Contact form or email for login, download, playback, or quiz-function issues. |
| Licensing or exam-policy question | Link students to current official exam resources and state that CTA cannot make eligibility decisions. |
| Emotional reassurance | Supportive recorded coaching, normalization of practice errors, and practical anxiety-management guidance. |

# 12. File Access, Security, and Internal Controls

| Resource | Student Access | CTA Internal Access | Control |
| --- | --- | --- | --- |
| Workbooks and Roadmaps | Yes | Yes | Download or online reading. |
| 17-Question Banks | Yes | Yes | Questions visible before answers; rationale after submission. |
| Comprehensive Forms A and B | Yes | Yes | Timed and sequentially released. |
| Student Rationale Guides | Controlled | Yes | Release only after the associated attempt. |
| Master Question-Bank Spreadsheets | No | Yes | Restricted internal storage. |
| Administrative Item Banks and Use Logs | No | Yes | Restricted internal storage. |
| Blueprint and QC Reports | No | Yes | Restricted internal storage. |
| Answer-Key Source Files | No | Yes | Never place in public downloads or searchable website folders. |

Security Principle Student convenience should never expose the master bank, item-status designations, pretest-style labels, answer-distribution controls, alternate-form pairs, or internal QC notes.

# 13. Website Functional Requirements

| Priority | Capability | Minimum Requirement |
| --- | --- | --- |
| Essential | Responsive lessons | Readable on desktop, tablet, and mobile. |
| Essential | File downloads | Reliable access to printable materials with clear names and version numbers. |
| Essential | Quiz scoring | Supports three- and four-option items, submission, scoring, and rationale release. |
| Essential | Timed exams | Supports long simulations, saved progress, section transitions, and final submission. |
| Essential | Progress tracking | Shows completed lessons, workbook banks, remediation, and simulations. |
| Essential | Accessible media | Captions, transcripts, keyboard navigation, and audio controls. |
| Strongly Preferred | Domain analytics | Shows strengths and weak areas after comprehensive forms. |
| Strongly Preferred | Attempt history | Stores score, date, time used, and response review. |
| Strongly Preferred | Conditional release | Locks Form B until Form A remediation is complete. |
| Optional Enhancement | Study reminders | Allows students to opt into scheduled email reminders. |

# 14. Implementation Phases

| Phase | Deliverables | Launch Value |
| --- | --- | --- |
| Phase 1: Course Shell and Files | Build Start Here, upload roadmaps and 12 workbooks, organize workbook sections, add downloads, and establish student navigation. | Creates a usable self-paced course immediately. |
| Phase 2: Online Question Banks | Enter all 17-question banks, configure scoring and rationale release, and test three-/four-option behavior. | Adds interactive learning and progress tracking. |
| Phase 3: Comprehensive Simulations | Build Forms A and B, timing, section rules, score summaries, remediation, and controlled rationale release. | Completes the core readiness system. |
| Phase 4: Core Multimedia | Produce eight shared strategy recordings plus seven LMFT and seven LCSW profession-specific recordings. | Creates the instructor-like coaching presence. |
| Phase 5: Workbook Companion Media | Produce one short video/audio lesson for each of the 24 workbooks. | Deepens engagement and reinforces topic-specific reasoning. |
| Phase 6: Enhancement Library | Add quick-reference sheets, flashcards, audio review playlists, readiness assessments, FAQs, and optional reminders. | Improves retention, convenience, and perceived program value. |

# 15. Immediate Production Priorities

Finalize this delivery plan as the governing website and multimedia architecture.

Create the shared Welcome to CTA Exam Success System script and slide outline.

Create the How to Use the 12 Workbooks and Question Banks script and slide outline.

Create the FIRST/NEXT/BEST/MOST Appropriate Questions strategy script and slide outline.

Create a reusable CTA video-script, slide, caption, transcript, and MP3 production template.

Map each of the 24 workbook sections to its website lesson, download, question bank, rationale, and companion-media placeholder.

Select or configure the website quiz and timed-exam functions before entering all comprehensive-form questions.

# 16. Final Program Decisions

| Decision | Approved Direction |
| --- | --- |
| Instructional Model | Fully self-paced; no live teacher or administrator is required for instruction. |
| Delivery | Online, downloadable/printable, and hybrid pathways are equally supported. |
| Assessment | One 17-question bank per workbook plus Forms A and B. |
| Feedback | Complete rationale and strategy guidance released after submission. |
| Multimedia | Short narrated slide videos with captions, transcripts, and audio-only versions when appropriate. |
| Student Support | Self-service instructional guidance plus technical support; no individualized licensing determinations. |
| Internal Controls | Master spreadsheets, administrative banks, use logs, and QC reports remain restricted CTA records. |

Next Production Set The first multimedia package should include three shared scripts: (1) Welcome to the CTA Exam Success System, (2) How to Use the 12 Workbooks and Question Banks, and (3) How to Read FIRST, NEXT, BEST, and MOST Appropriate Questions.

Internal CTA planning document. Exam-preparation programs are educational review products and do not guarantee passage of a licensing examination.