CTA LPCC NCMHCE EXAM PREPARATION PROGRAM

# NCMHCE 2027 Update Register

Controlled Review and Replacement Plan

Version 1.0 | August 3, 2026

Teaching Clinicians How to Think.

PURPOSE Protect current learners and prevent outdated exam-format claims by scheduling the transition from the current 11-case NCMHCE to the specifications effective July 1, 2027.

# 1. Controlling Change

| Control | Approved Entry |
| --- | --- |
| Effective date | July 1, 2027 |
| Case structure | 10 case studies; each case remains divided into three sections. |
| Item count | 130-150 total items, including 30-50 field-test items. |
| Testing time | 225 minutes for examination items; optional 15-minute break halfway through the examination. |
| Review control | Candidates may review within each half; after submitting the first half and beginning the break, they cannot return. |
| Score reporting | Scaled score range 100-500; passing point 360. |

# 2. New Domain Blueprint

| Domain | Weight |
| --- | --- |
| Professional Development & Counselor Self-Awareness | 15% |
| Intake & Assessment | 18% |
| Treatment Planning & Continuity of Care | 15% |
| Provision of Counseling Interventions | 20% |
| Indirect Client Care | 12% |
| Legal & Ethical Compliance | 20% |

# 3. Assets Requiring Review or Replacement

| Asset group | Required action | Release control |
| --- | --- | --- |
| WB1 exam strategy | Replace current 11-case and section-by-section navigation instructions with 10-case and half-exam review controls. | New edition required |
| WB2-WB12 workbooks | Map each objective, framework, example, and knowledge check to the six new domains; update domain language where applicable. | Content review and version update |
| 12 workbook banks | Retag each item to the new domain blueprint and confirm one-best-answer quality under the revised specifications. | New controlled metadata |
| Checkpoints 1-3 | Rebalance cumulative coverage to the new domains without introducing future simulation items. | Rebuild or formally revalidate |
| Forms A and B | Replace 11-case current-format forms with 10-case forms, half-exam review control, new domain weights, and 100-500 practice-score explanation. | New forms required |
| Form A remediation | Update domain scoring, case mapping, and corrected-rule prompts. | Revision required |
| Quick reference, tracker, roadmap, FAQ | Replace all dated structure, timing, break, review-lock, domain, and scoring claims. | Revision required |
| Website/LMS copy | Update inclusions, exam facts, FAQs, SEO, and effective-date notices before selling to July 2027 examinees. | Publication blocker |

# 4. Controlled Timeline

| Target date | Action | Completion evidence |
| --- | --- | --- |
| November 2026 | Quarterly official-source check. Confirm no interim NBCC changes. | Source-control log |
| February 2027 | Second official-source check; freeze the affected-asset inventory. | Approved transition inventory |
| March 2027 | Complete new-domain crosswalk and workbook revision blueprint. | Crosswalk and change list |
| April 2027 | Revise workbooks, banks, checkpoints, and support tools. | Draft replacement set |
| May 2027 | Build new 10-case Forms A and B, rationales, scoring tools, and remediation. | Synchronized simulation set |
| June 2027 | Render, accessibility review, source verification, LMS testing, and cutover rehearsal. | Final QA and implementation report |
| July 1, 2027 | Publish the revised edition and archive current-format files from learner view. | Owner approval and launch record |

# 5. Learner and Sales Controls

Do not market the current-format edition to a candidate whose examination date is on or after July 1, 2027 unless the revised edition has been released.

During the transition, display the examination-date question before enrollment or provide a clear routing notice.

Keep current-format and 2027-format simulations, keys, trackers, and score reports in separate controlled folders.

Do not interpret a CTA raw score as an NBCC scaled score. The official 2027 scale is 100-500 with a passing point of 360.

Record every replacement filename, version, approval date, and archive action in the file-control register.

# 6. Final Sign-Off

| Field | Entry |
| --- | --- |
| Transition owner | ________________________________________ |
| Content reviewer | ________________________________________ |
| Source verification date | ________________________________________ |
| Revised package version | ________________________________________ |
| Owner approval | ________________________________________ |