LPCC NCMHCE EXAM PREPARATION PROGRAM

Final Publication Readiness Audit & Approval Record

Version 1.0 | July 2026 | Exam Preparation Program | No CE Credit

AUDIT DETERMINATION The LPCC NCMHCE curriculum, assessment sequence, final Form B simulation, and core student-administration guides are complete. The package is approved to move into LMS build and testing. It is not yet approved for public sale or learner release until the exact course folder is reconciled, duplicate files are archived, the LMS workflow is tested, public systems are synchronized, and the final approver signs this record.

Current status: CURRICULUM COMPLETE - APPROVED FOR LMS BUILD

Public release status: PENDING FINAL IMPLEMENTATION APPROVAL

Teaching Clinicians How to Think.

1. Program Identity and Release Classification

| Field | Controlling Entry |
| --- | --- |
| Program title | CTA LPCC NCMHCE Exam Preparation Program |
| Primary learner | APCCs and other eligible candidates preparing for the NCMHCE |
| Program type | Self-paced, asynchronous licensure examination preparation |
| Credit status | No continuing-education credit |
| Curriculum status | Complete |
| Implementation status | Approved for LMS build and testing |
| Public release status | Pending final implementation approval |
| Current-format control | Review and update before use for examinations administered on or after July 1, 2027 |

2. Corrections and Administrative Gaps Resolved

| Previously Open Item | Resolution | Status |
| --- | --- | --- |
| Workbook 12 running header | Corrected from the Workbook 10 header to “CTA LPCC Workbook 12 - California Legal, Ethical & Professional Practice” on all interior pages; the 20-page workbook was rerendered and visually reviewed. | Resolved |
| Student Start Here roadmap | Completed with the WB1-WB12 sequence, checkpoint gates, Form A remediation, Form B release sequence, final-week guidance, and 10-, 14-, and 18-week routes. | Complete |
| Student FAQ and support guide | Completed with navigation, scoring, rationale release, troubleshooting, official-source reminders, and support boundaries. | Complete |
| LMS implementation guide | Completed with lesson order, release controls, lock rules, controlled-answer sequencing, archive expectations, and implementation checks. | Complete |
| Form B candidate/rationale synchronization | Automated audit completed against the controlling candidate and rationale files. | Verified |

3. Form B Synchronization Audit

CONTROLLED FORM B PAIR The July 28, 2026, 04:46 upload pair is the working controlling candidate/rationale set. Earlier identical-name copies should be archived or labeled as duplicates during course-folder reconciliation.

| Audit Test | Result | Status |
| --- | --- | --- |
| Candidate question sequence | Questions 1-143 are present with no missing or duplicate numbers. | Verified |
| Candidate options | Every question contains options A, B, C, and D. | Verified |
| Detailed rationale sequence | Rationale entries 1-143 are present. | Verified |
| Correct-answer fields | All 143 rationale entries contain one correct-answer letter. | Verified |
| Compact answer key | The compact key contains all 143 answers. | Verified |
| Key-to-rationale agreement | All 143 compact-key letters match the detailed-rationale answer letters. | Verified |
| Question-stem agreement | All 143 rationale question stems match the candidate examination stems. | Verified |
| Correct-option text agreement | For every item, the rationale’s correct-answer text matches the corresponding candidate option. | Verified |

4. Publication Package Readiness Matrix

| Package Area | Audit Determination | Status |
| --- | --- | --- |
| Twelve student workbooks | Program sequence and titles established; corrected WB12 is directly verified. Exact current filename/version for WB1-WB11 must be confirmed in the release folder. | Directory confirmation required |
| Twelve practice-bank candidate forms | Program architecture established; exact current copies must be mapped to the release folder. | Directory confirmation required |
| Twelve controlled rationale forms | Program architecture established; exact current copies must be mapped to the controlled folder. | Directory confirmation required |
| Three cumulative checkpoints | Sequence established after WB4, WB8, and WB12; candidate/rationale pairs must be confirmed in the release folder. | Directory confirmation required |
| Form A candidate and rationales | Form A sequence is established; final controlling pair must be confirmed in the release folder. | Directory confirmation required |
| Form A remediation workbook | Present in the established program sequence and required before Form B. | Complete |
| Form B candidate and rationales | Controlling pair identified and fully synchronized. | Verified |
| Readiness tracker and study routes | Present and incorporated into the Start Here roadmap. | Complete |
| Flashcards and audio review | Established as program reinforcement assets; exact release-folder copies must be confirmed. | Directory confirmation required |
| Quick-reference/rapid-review library | Established in the program sequence; exact release-folder files must be confirmed. | Directory confirmation required |
| Student Start Here roadmap | Completed. | Complete |
| Student FAQ and support guide | Completed. | Complete |
| LMS implementation and release-control guide | Completed. | Complete |
| Master Course Catalog and pricing catalog | Still show the LPCC program as in development/activating upon release; update after LMS testing and final approval. | Pending |

5. Remaining Conditions Before Public Release

| No. | Condition | Completion Standard | Status |
| --- | --- | --- | --- |
| 1 | Release-folder reconciliation | Create one exact inventory showing the current filename, version, learner/controlled classification, and location of every workbook, bank, checkpoint, simulation, review resource, media asset, and administration document. | Required |
| 2 | Duplicate and archive control | Retain one controlling copy of each asset. Move all earlier, duplicate, draft, or superseded files into a clearly labeled archive. | Required |
| 3 | LMS build and testing | Upload the approved files and test lesson order, progression locks, rationale release, Form A remediation gate, Form B access, downloads, mobile view, access period, and support links. | Required |
| 4 | Public-system synchronization | After LMS testing, update the Master Course Catalog, pricing catalog, website, LMS product listing, product image, title, launch price, access period, and support/update terms. | Required |
| 5 | 2027 update register | Create a controlled review schedule for all workbooks, banks, checkpoints, simulations, scoring sheets, official-source reminders, and public claims affected by the July 1, 2027 NCMHCE specifications. | Required |
| 6 | Final approving-authority signoff | The Founder/CEO or designated final approver confirms that all conditions are satisfied and changes the release classification to Approved for Publication. | Required |

6. Approval Stages

| Approval Stage | Determination | Status |
| --- | --- | --- |
| Curriculum completeness | All required instructional and assessment content through Form B is present; no additional core workbook or required simulation is indicated. | Approved |
| Assessment integrity | Form B question, option, key, and rationale synchronization passed. | Approved |
| Student administration | Start Here, FAQ, and LMS implementation guides are complete. | Approved |
| LMS build authorization | The reconciled package may proceed into LMS implementation and testing. | Approved for LMS Build |
| Public learner release | Requires completion of the six conditions in Section 5 and final approver signature. | Pending |

BOTTOM LINE The LPCC NCMHCE exam-preparation curriculum is complete. The remaining work is implementation control—not additional educational content. The program should now move into release-folder reconciliation and LMS build/testing.

7. Final Approval Record

| Field | Entry |
| --- | --- |
| Curriculum and assessment content complete | ☒ Yes ☐ No |
| Workbook 12 correction verified | ☒ Yes ☐ No |
| Form B synchronization audit passed | ☒ Yes ☐ No |
| Student Start Here guide complete | ☒ Yes ☐ No |
| Student FAQ complete | ☒ Yes ☐ No |
| LMS implementation guide complete | ☒ Yes ☐ No |
| Exact release-folder inventory reconciled | ☐ Yes ☒ No |
| Duplicate/superseded files archived | ☐ Yes ☒ No |
| LMS and download testing completed | ☐ Yes ☒ No |
| Catalog, pricing, website, and LMS listing synchronized | ☐ Yes ☒ No |
| 2027 update register created | ☐ Yes ☒ No |
| Current release classification | ☐ Draft ☐ Under Review ☒ Approved for LMS Build ☐ Approved for Publication ☐ Archived |
| Final approved by | ____________________________________________ |
| Final approval date | ____________________________________________ |
| Released version | ____________________________________________ |
| Final comments | ________________________________________________________________________________ ________________________________________________________________________________ |

8. Controlled Files Used for This Audit

CTA_LPCC_Comprehensive_Simulation_Form_B_143_Question_Candidate_Exam_v1.0.docx

CTA_LPCC_Comprehensive_Simulation_Form_B_143_Question_Answer_Rationales_v1.0.docx

CTA_LPCC_WB12_California_Legal_Ethical_Documentation_Technology_and_Professional_Practice_Student_Workbook_v1.0.docx (corrected)

CTA_LPCC_Student_Start_Here_Roadmap_and_10_14_18_Week_Study_Schedules_v1.0.docx

CTA_LPCC_Student_FAQ_and_Self_Service_Support_Guide_v1.0.docx

CTA_LPCC_LMS_Implementation_and_Release_Control_Guide_v1.0.docx

CTA_LPCC_NCMHCE_Prepublication_Master_Index_and_Gap_Report_v1.0.docx

CTA_Master_Course_Catalog_v2.0.docx

CTA_Master_Pricing_Subscription_and_Bundle_Catalog_v3.0.docx